## Bugs and small tasks
Description | Priority | Estimate in days | Status | Dependencies | Other notes
Gloves glow when an enemy is around or when a power up is used |  |  |  |  | Runes light up when enemies are nearby, or you are in heroic or legendary modes or you have purchased the coin doubler, or you are using a power-up

## Stories
Description | Priority | Estimate in days | Status | Dependencies | Other notes
Rate this app | High | 2 |  | Use asset store bundle
Native Sharing | High | 1 |  | Use asset store bundle
Store - iTunes | Essential | 5 |  | Update to 5.4 first
Rewarded Ads | Medium | 5
Daily reward | Medium | 4
Asset Bundle management | Medium | 5
UI makeover | High | 5 |  | Use final art
Store UI | High | 5
Sound fx | High | 4
Music | Medium | 1
Dynamic music | Low | 1.5 |  |  | Play combat music when there are enemies around
Voice Overs | Low | 2 |  |  | English only initially
Translations | Medium | 1 |  |  | Support English and French only for now
Android version | Essential | 15
Game Icon | Essential | 0.5
Tutorial | Essential
Facebook Tasks
If not connected to Facebook, offer to connect
If not connected to Internet
Publish Action permissions
Invite Friends popup
Update to latest Facebook SDK
Ask Friends for lives
Message Center
Connect to FB reminder popup
Update to Unity 5.4
Local notifications on day 3 and 8
Game Center
Progress indicator
DLC management
Link to Facebook community page
Difficulty Levels
Performance - improve FPS
Performance - lower build size
Time of Day
Fairy Sight powerup
Turn back time IAP
Analytics
Hero stats |  |  |  |  | Number of times revived, time to complete, etc
Video replay |  |  |  |  | Everyplay, ReplayKit for IOS
More hero model options
Hero's look customizable
Secret lair Easter egg
Ziplining
Endless, distance-based mode that gets unlocked after main quest is completed
Collect for Runes to be able to activate Cullis Gate
Loading Menu tips
Fortune Teller gipsy caravan |  |  |  |  | Subsribe to newsletter, get quirky horoscope
Keep troll as pursuier or simply use as an enemy?
Endless runner mode
Make tiles inactive after t-junction
Keep only one tile per type in recycle list and try destroying others
Add a way to tag tiles as suitable for endless running with a weight system |  |  |  |  | isLandmark, isGoodForEndless, probability of apperance
New personal high score message in-game
Have a high score per theme
Have a leaderboard on gamecenter per theme
Have a challenge a friend mode |  |  |  |  | also challenge non-app users
Code Message center - display challenges and lives received
Code new pre-level popup
Code new post-level popup
Code new save me popup
Code selecting theme for endless running |  |  |  |  | Maybe as a scrollable bar
Inform user when he has completed an episode, that it is now unlocked for endless running

## Content
Description | Priority | Estimate in days | Status | Dependencies | Other notes
The Dark Tower |  |  |  |  | Includes tutorial
Add Malificent-style forest
Tanglewood
Add village
Mirror Scene with taste of hell
Elfland
Dreadknot Cemetery
Jungle of Tikirara
Macaw
Add stumbles: roots and rocks
Add objects in middlle of the path
Zaphir's Cave
Hell
Frozen Wasteland
Wait out the unatural storm
Lair of the Dragon
End of game cut-scene |  |  |  |  | 4-post bed, or bench
Treasure Island
Character Gallery

## UI
Have different images for each episode
Display Episode difficulty in pre-level popup
Effects and transitions