## Bugs and small tasks
Description | Priority | Estimate in days | Status | Dependencies | Other notes
Gloves glow when an enemy is around or when a power up is used |  |  |  |  | Runes light up when enemies are nearby, or you are in heroic or legendary modes or you have purchased the coin doubler, or you are using a power-up

## Stories
Description | Priority | Estimate in days | Status | Dependencies | Other notes
Rate this app | High | 2 |  | Use asset store bundle
Native Sharing | High | 1 |  | Use asset store bundle
Store - iTunes | Essential | 5 |  | Update to 5.4 first
Rewarded Ads | Medium | 5
Daily reward | Medium | 4
Asset Bundle management | Medium | 5
UI makeover | High | 5 |  | Use final art
Store UI | High | 5
Sound fx | High | 4
Music | Medium | 1
Dynamic music | Low | 1.5 |  |  | Play combat music when there are enemies around
Voice Overs | Low | 2 |  |  | English only initially
Translations | Medium | 1 |  |  | Support English and French only for now
Android version | Essential | 15
Game Icon | Essential | 0.5
Tutorial | Essential
Facebook Tasks
If not connected to Facebook, offer to connect
If not connected to Internet
Publish Action permissions
Invite Friends popup |  |  | Almost done | needs App store URL
Update to latest Facebook SDK |  |  | DONE
Ask Friends for lives
Message Center |  |  | IN PROGRESS
Connect to FB reminder popup |  |  | DONE
Update to Unity 5.4 |  |  | DONE
Local notifications on day 3 and 8
Game Center
Progress indicator
DLC management
Link to Facebook community page
Difficulty Levels
Performance - improve FPS
Performance - lower build size
Time of Day | Low
Fairy Sight powerup
Turn back time IAP
Analytics
Hero stats | Low |  |  |  | Number of times revived, time to complete, etc
Video replay | Low |  |  |  | Everyplay, ReplayKit for IOS
More hero model options | Low
Hero's look customizable | Low
Secret lair Easter egg | Low
Ziplining | Low |  | IN PROGRESS |  | Needs zipline animations and a bit more tweaking
Endless, distance-based mode that gets unlocked after main quest is completed |  |  | IN PROGRESS
Collect for Runes to be able to activate Cullis Gate
Loading Menu tips | High
Fortune Teller gipsy caravan | Low |  |  |  | Subsribe to newsletter, get quirky horoscope
Endless runner mode
Make tiles inactive after t-junction
Keep only one tile per type in recycle list and try destroying others
New personal high score message in-game
Have a high score per theme
Have a leaderboard on gamecenter per theme
Have a challenge a friend mode | High |  | IN PROGRESS |  | also challenge non-app users
Code Message center - display challenges and lives received | High |  | IN PROGRESS
Code new pre-level popup |  |  | IN PROGRESS
Code new post-level popup |  |  | IN PROGRESS
Code new save me popup
Inform user when he has completed an episode, that it is now unlocked for endless running
Improve endless mode by using sequences of tiles that make senses together instead of unique tiles that often repeat
Challenges
Have a challenge board |  |  |  |  | Challenger, episode, their score, your score, play, etc.
Have challenge modes |  |  |  |  | No lives, no powerups, etc
Code challenge overlay in or over EndlessPostLevel popup with results |  |  |  |  | i.e. you beat Bob, Suzie and 2 other firends. Congratulations.
Have Lily give you a daily challenge
Message Center
Number of messages often incorrect
Better handling of delay between a processed message and a deleted one
Revisit stumbles (which dont work well and are hard to see) and the role of the troll. |  |  |  |  | Maybe troll runs after you only for first level.

## Content
Description | Priority | Estimate in days | Status | Dependencies | Other notes
The Dark Tower |  |  |  |  | Includes tutorial
Add Malificent-style forest
Tanglewood
Add village
Mirror Scene with taste of hell
Elfland
Dreadknot Cemetery
Jungle of Tikirara
Macaw
Add stumbles: roots and rocks
Add objects in middlle of the path
Mines of Karentur
Code getting one of 3 magical gifts |  |  |  |  | Like immune to missiles, immune to swords and immune to obstacles. Make runes glow on glove
Code falling into hell |  |  |  |  | Fairy message before: Is it just me or did someone just crank the heat
Hell
Frozen Wasteland
Wait out the unatural storm
Lair of the Dragon
End of game cut-scene |  |  |  |  | 4-post bed, or bench
Treasure Island
Character Gallery

## UI
Have different images for each episode
Display Episode difficulty in pre-level popup
Effects and transitions