## Bugs and small tasks
Description | Priority | Estimate in days | Status | Dependencies | Other notes

## Stories
Description | Priority | Estimate in days | Status | Dependencies | Other notes
Rate this app | High | 2 |  | Use asset store bundle
Native Sharing | High | 1 |  | Use asset store bundle
Store - iTunes | Essential | 5 |  | Update to 5.4 first
Rewarded Ads | Medium | 5
Daily reward | Medium | 4
Asset Bundle management | Medium | 5
UI makeover | High | 5 |  | Use final art
Store UI | High | 5
Sound fx | High | 4
Music | Medium | 1
Voice Overs | Low | 2 |  |  | English only initially
Translations | Medium | 1 |  |  | Support English and French only for now
Android version | Essential | 15
Game Icon | Essential | 0.5
Tutorial | Essential
Facebook Tasks
If not connected to Facebook, offer to connect
If not connected to Internet
Publish Action permissions
Invite Friends popup
Update to latest Facebook SDK
Ask Friends for lives
Message Center
Update to Unity 5.4
Local notifications on day 3 and 8
Game Center
Progress indicator
DLC management
Link to Facebook community page
Difficulty Levels
Performance - improve FPS
Performance - lower build size
Time of Day
Fairy Sight powerup
Turn back time IAP
Analytics

## Content
Description | Priority | Estimate in days | Status | Dependencies | Other notes
The Dark Tower |  |  |  |  | Includes tutorial
Add Malificent-style forest
Tanglewood
Add village
Mirror Scene with taste of hell
Elfland
Dreadknot Cemetery
Jungle of Tikirara
Zaphir's Cave
Hell
Frozen Wasteland
Wait out the unatural storm
Lair of the Dragon
Treasure Island
Character Gallery

## UI
Have different images for each episode
Display Episode difficulty in pre-level popup
Effects and transitions